## Sheet2 (hidden)
Sprint | Commited | Completed | Recommended | Hours | Mult Factor | Percent of Reg Sprint | Weighted Completion
Wall-E | 223 | 142 |  | 96 | 125% | 80% | 177.5
Data | 166 | 105 | 138.2917 | 116 | 103.4% | 96.67% | 108.6207
Current |  |  | 108.6207 | 120 | 100% | 100%
Current
Person | Capacity | Points
Kyle | 100% | 36.2069
Kevin | 100% | 36.2069
Alfie | 10% | 3.6207
New Recommended |  | 76.0345
# People | 3
TODO:
Take into account capacity of previous sprints
Wall-E | 223 | 142 |  | 96 | 125% | 80% | 177.5

## AVG
Average Points per Person per Hour |  | Seed value
AVG for Sprint #1 | 0.25 | 0.25
AVG for Sprint #2 | 0.24265
AVG for Sprint #3 | 0.26226

## Sprint #3 - upcoming
Sprint Name | Sprint #3 | Total Person Hours: | 456 |  |  | Helper: Enter the number of hours to get the equivilent capacity
Commited |  | Weighted Completed | -16 |  |  | Hours | 8
Commited With Carry IN | -16 | Point/Person Hour | -0.035088 |  |  | Capacity: | 10%
Completed
Completed With Carry IN/OUT | -16
Hours in Current Sprint | 80 | Person | Capacity | Hours | Un-Weighted Recommendation | Carry Out | Carry In | Recommendation (With Carry Over)
Hours in Full Sprint | 80 | Sarah | 100% | 80 | 19.4118 |  | 0 | 19.4118
|  | Brian | 100% | 80 | 19.4118 |  | 0 | 19.4118
Mult Factor | 100% | Jim | 90% | 72 | 17.4706 |  | 8 | 25.4706
Rec Pt/PHour | 0.24265 | Louise | 100% | 80 | 19.4118 |  | 3 | 22.4118
Total Person Hours | 456 | Rikki | 100% | 80 | 19.4118 |  | 0 | 19.4118
Weighted Rec | 110.6471 | Eric | 80% | 64 | 15.5294 |  | 5 | 20.5294
|  |  |  | 0 | 0 |  | 0 | 0
Green = Fill out at start of sprint
Red = Fill out at end of sprint
[6 empty] | 0 | 16
Carry OUT = Tickets we should get credit for because they're "dev done" | Carry IN = Last sprint's carry out
but still need to be tracked in jira
possibly for QA

## Sprint #2 - completed
Sprint Name | Sprint #2 | Total Person Hours: | 372.24 |  |  | Helper: Enter the number of hours to get the equivilent capacity
Commited | 103 | Weighted Completed | 112.2222 |  |  | Hours | 8
Commited With Carry IN | 93 | Point/Person Hour | 0.30148 |  |  | Capacity: | 11.11%
Completed | 95
Completed With Carry IN/OUT | 101
Hours in Current Sprint | 72 | Person | Capacity | Hours | Un-Weighted Recommendation | Carry Out | Carry In | Recommendation (With Carry Over)
Hours in Full Sprint | 80 | Sarah | 100% | 72 | 18 | 0 | 5 | 23
|  | Brian | 100% | 72 | 18 | 0 | 2 | 20
Mult Factor | 111.1% | Jim | 89% | 64.08 | 16.02 | 8 | 0 | 16.02
Rec Pt/PHour | 0.25 | Louise | 78% | 56.16 | 14.04 | 3 | 0 | 14.04
Total Person Hours | 372.24 | Rikki | 100% | 72 | 18 | 0 | 0 | 18
Weighted Rec | 93.06 | Eric | 50% | 36 | 9 | 5 | 3 | 12
|  |  |  | 0 | 0 | 0 | 0 | 0
Green = Fill out at start of sprint
Red = Fill out at end of sprint
[6 empty] | 16 | 10
Carry OUT = Tickets we should get credit for because they're "dev done" | Carry IN = Last sprint's carry out
but still need to be tracked in jira
possibly for QA

## Sprint #1 - completed
Sprint Name | Sprint #1 | Total Person Hours: | 408 |  |  | Helper: Enter the number of hours to get the equivilent capacity
Commited | 102 | Weighted Completed | 96 |  |  | Hours | 8
Commited With Carry IN | 102 | Point/Person Hour | 0.23529 |  |  | Capacity: | 10%
Completed | 86
Completed With Carry IN/OUT | 96
Hours in Current Sprint | 80 | Person | Capacity | Hours | Un-Weighted Recommendation | Carry Out | Carry In | Recommendation (With Carry Over)
Hours in Full Sprint | 80 | Sarah | 100% | 80 | 20 | 5 | 0 | 20
|  | Brian | 90% | 72 | 18 | 2 | 0 | 18
Mult Factor | 100% | Jim | 70% | 56 | 14 | 0 | 0 | 14
Rec Pt/PHour | 0.25 | Louise | 100% | 80 | 20 | 0 | 0 | 20
Total Person Hours | 408 | Rikki | 50% | 40 | 10 | 0 | 0 | 10
Weighted Rec | 102 | Eric | 100% | 80 | 20 | 3 | 0 | 20
|  |  | 0% | 0 | 0 | 0 | 0 | 0
Green = Fill out at start of sprint
Red = Fill out at end of sprint
[6 empty] | 10 | 0
Carry OUT = Tickets we should get credit for because they're "dev done" | Carry IN = Last sprint's carry out
but still need to be tracked in jira
possibly for QA